## Missing Info
Missing Info ID | Section | What Is Missing? | Why It Is Needed | Who Needs To Provide It | Deadline | Priority | Status | Answer / Final Info | Notes
MI-ONSITE-001 | Contacts / Travel | Confirm Eve Dusek name, role, and contact details. | Approved display name is Eve Dusek; role currently tracked as COO of Aream & Co. | Samuel / Aream & Co. |  | High | Needs Confirmation |  | Do not use the old name in live display unless confirmed as a separate person.
MI-ONSITE-002 | Who Do I Call / Emergency | Health & Safety owner and emergency escalation process. | Who Do I Call needs explicit Health & Safety coverage. | Samuel / Chris / Venue |  | High | Needs Confirmation |  | Include phone, WhatsApp, venue contact, and escalation notes.
MI-ONSITE-003 | Locations / Maps | Venue map, exact internal pins, room layouts, seating plans, and Google Maps links. | Location cards and call sheet need exact maps without guessing. | Venue / Operations |  | High | Needs Confirmation |  | Use Google Maps Link Needed / Exact pin needed until supplied.
MI-ONSITE-004 | Weather | Confirm final weather coordinate / event hotel pin. | Open-Meteo is using Six Senses Ibiza / Xarraca Bay coordinates as a temporary confirmed-nearby point. | Samuel / Venue |  | Medium | Needs Confirmation |  | Weather location needs confirmation remains in notes.
MI-ONSITE-005 | HORIZONS House | Display cabinet image. | Reception Display section needs the glass display cabinet image. | Creative / Guest Experience |  | Medium | File Needed |  | Placeholder remains on site.
MI-ONSITE-006 | Room Drops | Confirm Pulsio / Poltio product name and room-drop placement. | Review notes mention Poltio; source image appears massage-gun/Pulsio-like. | Samuel / Guest Experience |  | Medium | Needs Confirmation |  | Do not finalize naming until confirmed.
MI-ONSITE-007 | Guest Materials | Crew shirts data/image confirmation. | Current crew shirt item may be incorrect. | Samuel / Guest Experience |  | Medium | Needs Confirmation |  | Flagged on site.
MI-ONSITE-008 | Speakers / Podcast | Final speaker content and podcast guest/company/prep ownership. | Speaker grouping and podcast episode cards need final content. | Samuel / Production |  | High | Needs Confirmation |  | Includes guest runner, prep owner, microphone and powder/makeup checks.
MI-ONSITE-009 | Rehearsals | HORIZONS Studio rehearsal timing for 8 June. | Placeholder added with Time needed. | Production |  | High | Needs Confirmation |  | Confirm required people and owner.
MI-ONSITE-010 | Signage / Wayfinding | Wayfinding artwork, A1 boards, three totem locations, two wall foam board locations, and placement map. | Clownfish need exact install placement. | Creative / Clownfish |  | High | File Needed |  | Site has placeholders for Map Needed / Location Needed / Placement Needed.
MI-ONSITE-011 | Staff / Cvent / Slack | Staff corrections, Cvent export, and Slack production routing approval. | Admin/developer setup is ready but should not be activated broadly without approval. | Samuel / Chris |  | High | Needs Confirmation |  | Production Slack routes remain disabled/test-mode until approved.

## Questions To Answer
Question ID | Section | Question | Context | Who Should Answer | Answer | Decision / Outcome | Priority | Status | Date Resolved | Notes
Q-ONSITE-001 | Weather / Location | Is the Open-Meteo coordinate the exact event hotel pin or only a nearby Six Senses Ibiza reference? | Current site uses Six Senses Ibiza / Xarraca Bay coordinates and labels final pin as needing confirmation. | Samuel / Venue |  |  | Medium | Needs Confirmation
Q-ONSITE-002 | Slack | When should production Slack routes be activated beyond #horizons-test? | Website supports channel selection but production webhooks should not be enabled without approval. | Samuel / Chris |  |  | High | Needs Confirmation
Q-ONSITE-003 | Room Drops | Should the product be displayed as Pulsio, Poltio, or another approved name? | Latest notes used Poltio; asset resembles massage-gun/Pulsio item. | Guest Experience |  |  | Medium | Needs Confirmation

## Staff Cleanup 2026-06-01
Type | Area | Item | Status | Notes
Update | Staff Lists | Regroup staff into International Collective / I.N.C, Clownfish, Aream & Co., B Good, Performers, Hotel / Venue | Applied | Team-facing website data updated in content.json.
Update | Clownfish | Roles, dietary notes, and show-operative assignments | Applied | HORIZONS Hall: George Winning + Ryan Lowe. HORIZONS Studio: Alex Hudson + Nathan Rushmer.
Privacy | All team-facing views | Dates of birth excluded from website display and reports | Applied | No date values are included in this tracker note.
Missing | Contacts | Nathan Rushmer email | Needs Confirmation | Email Needed.
Missing | Contacts | George Winning email | Needs Confirmation | Email Needed.
Missing | Contacts | Joshua Millar email | Needs Confirmation | Email Needed.
Missing | Contacts | Ryan Lowe email and dietary final | Needs Confirmation | Email Needed; dietary TBC.
Missing | Contacts | Joachim Ridley-Barker email | Needs Confirmation | Email Needed.
Missing | Contacts | Alex Hudson email | Needs Confirmation | Email Needed.