## START HERE
HORIZONS Website Update Tracker
How to use this tracker
Add website changes into the correct tab. Use one row per request or update.
Set Status clearly. Only Approved or Ready for Codex rows should normally be applied to the live website.
Use Needs Confirmation when spelling, timing, ownership, files, or approvals are uncertain.
Codex uses this tracker to update the official website source data in content.json after review.
Website comments are discussion and feedback. They do not automatically change official website data.
Chris name rule: there is only one Chris, and his name is Chris Manoe.
HORIZONS Hall rule: do not use Farmers Market Stage.
Do not invent missing phone numbers, emails, files, timings, or approvals.
Excel cannot use / in tab names, so Image / Asset Updates is named Image + Asset Updates.
Allowed status values
New
Needs Confirmation
Approved
Ready for Codex
Added to Website
Rejected / Do Not Add
Waiting on Info
Complete

## Website Change Requests
Request ID | Date Added | Added By | Section | Current Website Text / Issue | Requested Change | Reason / Context | Priority | Status | Approved By | Notes
UX-ONSITE-001 | 2026-05-29 | Codex | Hero / Header | Visible hero repeated HORIZONS Ibiza 2026 beneath the official logo. | Remove repeated visible event title and centre hero content around the official logo. | Chris/Samuel onsite review: reduce duplication and keep the brand moment calmer. | High | Complete | Codex | Implemented in index.html/style.css; official event name remains in source metadata.
UX-ONSITE-002 | 2026-05-29 | Codex | Navigation | Leadership and admin sections were mixed together in a long navigation list. | Reorder navigation into Start, Operations, People, Programme, Guest Experience, and Admin groups. | Make mobile navigation easier for executives and onsite operators. | High | Complete | Codex | Decisions moved higher; admin/developer tools moved lower.
UX-ONSITE-003 | 2026-05-29 | Codex | Comments / Updates | Updates could be added but resolution/archiving needed clearer actions. | Add Mark Resolved, Archive, Reopen, Slack channel selector, and urgent preview to update threads. | Team needs to clear handled items without deleting history. | High | Complete | Codex | Shared backend remains source for updates; archive/history stays visible.
UX-ONSITE-004 | 2026-05-29 | Codex | Call Sheet | Weather and emergency cards stacked on desktop and top notes pushed the timeline down. | Use side-by-side weather/emergency cards on desktop, compact notes, day/date tabs, and current time marker. | Improve onsite call sheet scanning. | High | Complete | Codex | Weather cache key refreshed after coordinate/location correction.
UX-ONSITE-005 | 2026-05-29 | Codex | Programme Sections | Podcast, speakers, entertainment, playlists, location schedules, and restaurants needed clearer grouping. | Group podcast by day/episode; speakers by location/day; locations/restaurants by day; separate live entertainment from curated playlists. | Reduce scrolling and avoid mixing background music with live performers. | High | Complete | Codex | Detailed unknown podcast/speaker fields remain Needs Confirmation.
UX-ONSITE-006 | 2026-05-29 | Codex | Admin Tools | Admin-heavy sections were prominent in the main flow. | Move Cvent, Missing Files, Slack, Data Health, Duplicate Review, and Site Audit into the lower admin navigation group. | Keep the main team experience calmer. | Medium | Complete | Codex | Admin records remain available.
UX-ONSITE-007 | 2026-05-29 | Codex | HORIZONS Studio | Standalone HORIZONS Studio operational section was not useful. | Hide/remove standalone HORIZONS Studio section while retaining Studio as location/source/programme data. | Latest review requested removal of standalone section only. | Medium | Complete | Codex | HORIZONS Studio still appears in location schedules, speakers, rehearsals, call sheet, and data records.
WCR-R2-001 | 28 May 2026 | Codex | Navigation | Side progress index could stick around Red Flags. | Replace scroll spy with sticky-header aware active section tracking. | CEO round-two review | High | Added to Website | Codex | Implemented in script.js.
WCR-R2-002 | 28 May 2026 | Codex | Call Sheet | No dedicated Daily Call Sheet view. | Add Daily Call Sheet section rendered from schedule data. | CEO round-two review | High | Added to Website | Codex | Implemented in index.html/script.js.
WCR-R2-003 | 28 May 2026 | Codex | Cards | Travel, supplier, and content capture cards were too long. | Use compact default cards with expandable details. | CEO round-two review | High | Added to Website | Codex | Implemented in script.js/style.css.
WCR-SYNC-001 | 29 May 2026 | Codex | Schedule / Call Sheet | Latest workbook not fully reflected | Sync latest 310-row schedule, add Saturday 6 June, and use AM/PM display | Latest final schedule sync workbook | Critical | Added to Website | Codex | Applied to content.json; unresolved source gaps remain Needs Confirmation
WCR-SYNC-002 | 29 May 2026 | Codex | Guest Materials & Experience | Swag section too narrow | Expand to Guest Materials & Experience and add tote bags, crew shirts, easel boards, signage, menus | Latest user revision and assets | High | Added to Website | Codex | Assets linked; missing files remain placeholders
WCR-SYNC-003 | 29 May 2026 | Codex | Call Sheet | Weather needed | Add weather module placeholder for Six Senses Ibiza / Ibiza | Latest user revision | High | Added to Website | Codex | Live weather API/source still needed
REQ-SLACK-001 | 29 May 2026 | Codex | Slack Integration | Add Slack-safe source-of-truth communication layer with channel map and copy update actions | Add Slack section, channel mapping, and no-secret webhook guidance | Leadership feedback | High | Added to Website | Codex | Webhook URLs must be configured server-side only
REQ-LOC-001 | 29 May 2026 | Codex | Location Schedules | Need location-specific and restaurant-specific views | Add Location Schedules and Restaurant Schedules sections from master schedule data | Leadership feedback | High | Added to Website | Codex | Uses content.json locationSchedules and restaurantSchedules
REQ-CONTENT-001 | 29 May 2026 | Codex | Speakers / Cvent / Entertainment | Need speaker content, Cvent audit, entertainment, playlists, rehearsals and signage models | Add compact operational sections and data records | Leadership feedback | High | Added to Website | Codex | Unconfirmed data stays Needs Confirmation/File Needed

## Missing Information
Missing Info ID | Section | What Is Missing? | Why It Is Needed | Who Needs To Provide It | Deadline | Priority | Status | Answer / Final Info | Notes
MI-ONSITE-001 | Contacts / Travel | Confirm Eve Dusek name, role, and contact details. | Approved display name is Eve Dusek; role currently tracked as COO of Aream & Co. | Samuel / Aream & Co. |  | High | Needs Confirmation |  | Do not use the old name in live display unless confirmed as a separate person.
MI-ONSITE-002 | Who Do I Call / Emergency | Health & Safety owner and emergency escalation process. | Who Do I Call needs explicit Health & Safety coverage. | Samuel / Chris / Venue |  | High | Needs Confirmation |  | Include phone, WhatsApp, venue contact, and escalation notes.
MI-ONSITE-003 | Locations / Maps | Venue map, exact internal pins, room layouts, seating plans, and Google Maps links. | Location cards and call sheet need exact maps without guessing. | Venue / Operations |  | High | Needs Confirmation |  | Use Google Maps Link Needed / Exact pin needed until supplied.
MI-ONSITE-004 | Weather | Confirm final weather coordinate / event hotel pin. | Open-Meteo is using Six Senses Ibiza / Xarraca Bay coordinates as a temporary confirmed-nearby point. | Samuel / Venue |  | Medium | Needs Confirmation |  | Weather location needs confirmation remains in notes.
MI-ONSITE-005 | HORIZONS House | Display cabinet image. | Reception Display section needs the glass display cabinet image. | Creative / Guest Experience |  | Medium | File Needed |  | Placeholder remains on site.
MI-ONSITE-006 | Room Drops | Confirm Pulsio / Poltio product name and room-drop placement. | Review notes mention Poltio; source image appears massage-gun/Pulsio-like. | Samuel / Guest Experience |  | Medium | Needs Confirmation |  | Do not finalize naming until confirmed.
MI-ONSITE-007 | Guest Materials | Crew shirts data/image confirmation. | Current crew shirt item may be incorrect. | Samuel / Guest Experience |  | Medium | Needs Confirmation |  | Flagged on site.
MI-ONSITE-008 | Speakers / Podcast | Final speaker content and podcast guest/company/prep ownership. | Speaker grouping and podcast episode cards need final content. | Samuel / Production |  | High | Needs Confirmation |  | Includes guest runner, prep owner, microphone and powder/makeup checks.
MI-ONSITE-009 | Rehearsals | HORIZONS Studio rehearsal timing for 8 June. | Placeholder added with Time needed. | Production |  | High | Needs Confirmation |  | Confirm required people and owner.
MI-ONSITE-010 | Signage / Wayfinding | Wayfinding artwork, A1 boards, three totem locations, two wall foam board locations, and placement map. | Clownfish need exact install placement. | Creative / Clownfish |  | High | File Needed |  | Site has placeholders for Map Needed / Location Needed / Placement Needed.
MI-ONSITE-011 | Staff / Cvent / Slack | Staff corrections, Cvent export, and Slack production routing approval. | Admin/developer setup is ready but should not be activated broadly without approval. | Samuel / Chris |  | High | Needs Confirmation |  | Production Slack routes remain disabled/test-mode until approved.

## Questions To Answer
Question ID | Section | Question | Context | Who Should Answer | Answer | Decision / Outcome | Priority | Status | Date Resolved | Notes
Q-ONSITE-001 | Weather / Location | Is the Open-Meteo coordinate the exact event hotel pin or only a nearby Six Senses Ibiza reference? | Current site uses Six Senses Ibiza / Xarraca Bay coordinates and labels final pin as needing confirmation. | Samuel / Venue |  |  | Medium | Needs Confirmation
Q-ONSITE-002 | Slack | When should production Slack routes be activated beyond #horizons-test? | Website supports channel selection but production webhooks should not be enabled without approval. | Samuel / Chris |  |  | High | Needs Confirmation
Q-ONSITE-003 | Room Drops | Should the product be displayed as Pulsio, Poltio, or another approved name? | Latest notes used Poltio; asset resembles massage-gun/Pulsio item. | Guest Experience |  |  | Medium | Needs Confirmation

## Schedule Updates
Schedule Update ID | Day / Date | Current Time | New Time | Current Title | New Title | Location | Owner | Support | Department | Status | Priority | Notes | Approved By | Website Update Status
CS-R2-001 | All event days | Current schedule data | Derived daily call sheet view | Daily Call Sheet confirmation | Daily Call Sheet confirmation | Various | Chris Manoe | Poppy Luck / I.N.C | Operations | Needs Confirmation | High | Confirm owner/support/supplier/content links for each day before final event use. | Chris Manoe | Ready for Codex

## Task Updates
Task Update ID | Task Title | Day / Date | Time | Owner | Support | Department | Location | Current Status | New Status | Notes / Update | Approved By | Website Update Status

## Contact Updates
Contact Update ID | Name | Correct Name | Role | Company / Team | Department | Phone | WhatsApp | Email | On-Site or Remote | Main Responsibility | Notes | Status | Approved By | Website Update Status
Chris Manoe rule: there is only one Chris. Do not add Chris Minot, CM, or Chris M.
CONTACT-SAMUEL-ROLE-001 | Samuel Price | Samuel Price | Podcast Lead / Executive Assistant to Chris Manoe / Website Development & Software Lead / Infrastructure & Systems Support Lead | HORIZONS | Leadership / Production / Systems |  |  |  | On-site / support | Podcast, Chris support, website/software, infrastructure/systems | Updated from latest leadership brief | Added to Website | Codex | Added to contact card and staff list

## Supplier Updates
Supplier Update ID | Supplier Name | Supplier Type | Contact Person | Phone | Email | Internal Owner | Day / Date | Arrival Time | Setup Time | Active Time | Location | Responsibility | Open Item / Question | Status | Notes | Approved By | Website Update Status
SUP-SYNC-001 | Mobile Casino / Poker | Supplier / Performer | Contact needed |  |  | Dawn Ramsden / BE GOOD | Wednesday 10 June |  |  |  | Arcade | Poker/casino setup | Confirm setup 15:00-16:00 vs later delivery and 33 chairs | Needs Confirmation | Added from final revision | Samuel / Dawn | Needs Confirmation
SUP-SYNC-002 | BE GOOD | Operations / Logistics | Ben Eddon-Carruthers / Cheryl Leno | See Contacts tab |  | Samuel Price | All event |  |  |  | Six Senses Ibiza / HORIZONS House | Room drops, logistics, guest materials | Confirm all day/time details and final file uploads | Needs Confirmation | Company spelling standardized as BE GOOD | Samuel | Added to Website

## Podcast Updates
Podcast Update ID | Day / Date | Time | Guest | Host | Crew | Location | Production Needs | Current Status | New Status | Notes | Approved By | Website Update Status

## Content Capture Updates
Content Update ID | Day / Date | Time | Moment / Capture Item | Content Type | Person Responsible | Support | Location | Department | Priority | Status | Notes | Approved By | Website Update Status

## Documents + Links
Document ID | Document Title | Category | Day / Date | Description | File Name | File Link / URL | Owner | Status | Website Location | Notes
DOC-SYNC-001 | HORIZONS Website Final Schedule Sync Workbook | Source Data | All | Latest workbook source for website sync | horizons-website-final-schedule-sync-for-codex.xlsx | assets/documents/horizons-website-final-schedule-sync-for-codex.xlsx | Samuel Price | Added to Website | Documents / Source Data | Copied into assets/documents
DOC-SYNC-002 | HORIZONS Swag Delivery Brief | Swag / Guest Materials | All | Reference for room drops, swag, and guest materials | horizons-swag-delivery-brief.pdf | assets/documents/horizons-swag-delivery-brief.pdf | BE GOOD / HORIZONS team | Added to Website | Documents / Swag / Guest Materials | Copied into assets/documents
DOC-MISSING-FILES-001 | Missing Files Tracker | Source Data | All | Expanded missing files tracker for call sheets, Cvent, speaker content, signage, staff, entertainment, playlists, podcast, and venue files | content.json missingFiles |  | Samuel Price | Added to Website | Missing Files section | Keep approved files in Documents section

## Red Flags + Decisions
Item ID | Type | Section | Issue / Decision Needed | Why It Matters | Owner | Deadline | Current Status | Final Decision / Update | Approved By | Date Resolved | Website Update Status | Notes

## Image + Asset Updates
Asset ID | Section | Image / Asset Name | File Name | File Link / Location | Description / Caption | Alt Text | Status | Notes
ASSET-R2-001 | Brand / Hero | Official main HORIZONS logo | horizons-main-logo-black.png | assets/logos/horizons-main-logo-black.png | Primary hero/header logo source. | Official HORIZONS logo | Added to Website | Provided by Chris Manoe; do not modify.
ASSET-R2-002 | Swag / Room Drops / HORIZONS House | Swag reference image set | assets/images/swag/*.jpeg | assets/images/swag/ | Tote bag, notebook, bottle, charger, fragrances, eye mask, fan, caps, massager, pen, lanyard. | Approved swag reference images | Added to Website | Added to content.json visual sections.

## Completed Website Updates
Update ID | Source Tab | Summary of Update | Date Completed | Completed By | Website Section Updated | Commit Message | Notes
R2-001 | Website Change Requests | Round two navigation, Call Sheet, compact card, official logo, and swag image update | 28 May 2026 | Codex | Overview / Schedule / Call Sheet / Flights / Suppliers / Content / Swag | Refine HORIZONS call sheets, compact cards, brand styling, and trackers | Pending deployment confirmation.

## Staff Cleanup 2026-06-01
Type | Area | Item | Status | Notes
Update | Staff Lists | Regroup staff into International Collective / I.N.C, Clownfish, Aream & Co., B Good, Performers, Hotel / Venue | Applied | Team-facing website data updated in content.json.
Update | Clownfish | Roles, dietary notes, and show-operative assignments | Applied | HORIZONS Hall: George Winning + Ryan Lowe. HORIZONS Studio: Alex Hudson + Nathan Rushmer.
Privacy | All team-facing views | Dates of birth excluded from website display and reports | Applied | No date values are included in this tracker note.
Missing | Contacts | Nathan Rushmer email | Needs Confirmation | Email Needed.
Missing | Contacts | George Winning email | Needs Confirmation | Email Needed.
Missing | Contacts | Joshua Millar email | Needs Confirmation | Email Needed.
Missing | Contacts | Ryan Lowe email and dietary final | Needs Confirmation | Email Needed; dietary TBC.
Missing | Contacts | Joachim Ridley-Barker email | Needs Confirmation | Email Needed.
Missing | Contacts | Alex Hudson email | Needs Confirmation | Email Needed.