## START_HERE
Start here. This tab explains where to find critical operational information.
Instruction
Use HORIZONS_MASTER_EVENT_CONTROL_UPDATED.xlsx as the main source-of-truth workbook.
For phone numbers and WhatsApp links, use TEAM_CONTACTS.
For who to contact by issue, use WHO_DO_I_CALL.
Website display source is content.json; this workbook is the clean human-readable control copy.
Do not guess missing information. Use Needs Confirmation, At Risk, File Needed, or Awaiting Asset Upload.
Official spellings: Aream & Co. and BeGood. Keep Samuel Price and Samuel Hosier separate.

## MISSING_FILES_TRACKER
Missing files/assets tracker.
File Needed | Category | Owner | Needed For | Priority | Status | Notes | Slack Request Button / Channel
StudioBinder call sheet example | Call Sheet / Production | Samuel Price | Call sheet layout reference | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Current production call sheet | Call Sheet / Production | Samuel Price | Production operations | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Weather call sheet reference | Call Sheet / Production | Samuel Price | Weather module | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Final master schedule | Call Sheet / Production | Samuel Price | Schedule approval | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Ben’s document | Call Sheet / Production | Ben Eddon-Carruthers | Operations detail | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Production contact hierarchy | Call Sheet / Production | Samuel Price | Who Do I Call | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Crew call sheet layout | Call Sheet / Production | Samuel Price | Printable call sheet | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Cvent agenda export | Cvent / Event App | Samuel Price | Cvent comparison | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Cvent speaker/session export | Cvent / Event App | Samuel Price | Cvent comparison | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Cvent venue/location list | Cvent / Event App | Samuel Price | Cvent comparison | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Cvent meal/restaurant schedule | Cvent / Event App | Samuel Price | Cvent comparison | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Cvent attendee-facing copy | Cvent / Event App | Samuel Price | Cvent comparison | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Speaker list | Speaker / Deck Content | Samuel Price | Speaker content | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Speaker bios | Speaker / Deck Content | Samuel Price | Deck creation | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Speaker session titles | Speaker / Deck Content | Samuel Price | Website/Cvent comparison | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Speaker session descriptions | Speaker / Deck Content | Samuel Price | Deck creation | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Speaker deck copy | Speaker / Deck Content | Samuel Price | Deck creation | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Speaker notes | Speaker / Deck Content | Samuel Price | Call sheet | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Speaker rehearsal schedule | Speaker / Deck Content | Dawn Ramsden | Rehearsals | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Horizons Hall rehearsal schedule | Speaker / Deck Content | Dawn Ramsden | Rehearsals | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Horizons Studio rehearsal schedule | Speaker / Deck Content | Dawn Ramsden | Rehearsals | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Technical rehearsal schedule | Speaker / Deck Content | Clownfish | Technical production | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Gift card artwork | Artwork / Wayfinding | Chris Manoe | Print assets | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Wayfinding artwork | Artwork / Wayfinding | Chris Manoe | Venue signage | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Easel board artwork | Artwork / Wayfinding | Chris Manoe | Signage | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
A1 board artwork | Artwork / Wayfinding | Chris Manoe | Signage | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Natural totem artwork | Artwork / Wayfinding | Chris Manoe | Signage | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Signage placement map | Artwork / Wayfinding | Clownfish | Onsite setup | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Tote bag artwork | Artwork / Wayfinding | Chris Manoe | Guest materials | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Notebook artwork | Artwork / Wayfinding | Chris Manoe | Guest materials | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Room drop references | Artwork / Wayfinding | BeGood | Room drops | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Print specs | Artwork / Wayfinding | Clownfish | Print production | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Clownfish setup positioning instructions | Artwork / Wayfinding | Clownfish | Onsite placement | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Clownfish staff list | Staff / Suppliers | Clownfish | Staff lists | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Clownfish roles/responsibilities | Staff / Suppliers | Clownfish | Who Do I Call | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
INC staff list | Staff / Suppliers | Samuel Price | Staff lists | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
INC roles/responsibilities | Staff / Suppliers | Samuel Price | Who Do I Call | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
BeGood staff/contact details | Staff / Suppliers | BeGood | Supplier contacts | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Hotel key contacts | Staff / Suppliers | Six Senses | Venue contacts | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Supplier contact list | Staff / Suppliers | Dawn Ramsden | Suppliers | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
DJ Lindsey Evans details | Entertainment | Dawn Ramsden | Entertainment | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
DJ Parris Taylor details | Entertainment | Dawn Ramsden | Entertainment | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Conner Reeves details | Entertainment | Dawn Ramsden | Entertainment | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Christina Hizon details | Entertainment | Dawn Ramsden | Entertainment | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Dan the Man details | Entertainment | Dawn Ramsden | Entertainment | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Performer arrival times | Entertainment | Dawn Ramsden | Call sheet | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Sound check times | Entertainment | Clownfish | Call sheet | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Performance times | Entertainment | Dawn Ramsden | Schedule | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Technical riders | Entertainment | Clownfish | Production | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Hospitality requirements | Entertainment | Dawn Ramsden | Hospitality | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Curated playlist links | Playlists | Dawn Ramsden | Music schedule | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Playlist names | Playlists | Dawn Ramsden | Music schedule | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Music usage schedule | Playlists | Dawn Ramsden | Call sheet | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Start/stop ownership | Playlists | Dawn Ramsden | Music operations | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Backup playlist plan | Playlists | Dawn Ramsden | Contingency | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Final podcast schedule | Podcast | Samuel Price | Podcast | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Podcast guest list | Podcast | Samuel Price | Podcast | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Podcast run sheet | Podcast | Samuel Price | Podcast | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Presenter notes | Podcast | Samuel Price | Podcast | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Guest arrival/holding notes | Podcast | Samuel Price | Podcast | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Podcast technical notes | Podcast | Clownfish | Podcast | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Release forms | Podcast | Samuel Price | Podcast | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Restaurant/meal schedules | Venue / Restaurants | Dawn Ramsden | Restaurants | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Final menus | Venue / Restaurants | BeGood | Menus | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Dietary notes | Venue / Restaurants | BeGood | Menus | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Venue maps | Venue / Restaurants | Six Senses | Maps | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Floor plans | Venue / Restaurants | Six Senses | Layouts | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Seating plans | Venue / Restaurants | Dawn Ramsden | Seating |  | Added to Website | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Stage layouts | Venue / Restaurants | Clownfish | Technical | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents
Tommy’s Tunnel access/load-in notes | Venue / Restaurants | Clownfish | Load-in | High | File Needed | Add file/link when available. Keep unresolved until confirmed. | #horizons-documents

## DOCUMENTS_LINKS
Clean document library.
Document Name | Category | Owner | Status | File Link | Needed For | Related Website Section | Notes
HORIZONS Website Final Schedule Sync Workbook | Source Data | Samuel Price | On Track | assets/documents/horizons-website-final-schedule-sync-for-codex.xlsx |  |  | Latest workbook used to sync schedule, contacts, locations, menus, and data gaps.
HORIZONS Website & Runbook Revision PDF | Runbooks | Samuel Price | On Track | assets/documents/horizons-website-runbook-revisions.pdf |  |  | Latest revision notes and runbook review document.
HORIZONS Style Guide | Style Guide | Chris Manoe | On Track | assets/documents/horizons-style-guide.pdf |  |  | Official brand/style guide for visual identity, typography, colour, and layout direction.
HORIZONS Swag Delivery Brief | Swag / Guest Materials | BeGood / HORIZONS team | On Track | assets/documents/horizons-swag-delivery-brief.pdf |  |  | Reference for swag, room drops, HORIZONS House display, and guest materials.
HORIZONS Connect logo file | Brand / Logos | Chris Manoe | On Track | assets/logos/horizons-connect-black.png |  |  | Official logo asset.
Primary HORIZONS logo file | Brand / Logos | Chris Manoe | On Track | assets/logos/horizons-main-logo-black.png |  |  | Primary logo used in the website hero/header.
Selected in-room dining items | Menus | BeGood / Six Senses | On Track |  |  |  | Brava's Potatoes; Farmers Chicken Salad; Xarraca Salad; Beef Burger; Chicken Sandwich; Sweet Potato Fries; Seasonal Fruit Platter
Food allergen key | Menus | BeGood / Six Senses | On Track |  |  |  | N Nuts; LU Lupin; D Dairy; E Eggs; F Fish; C Celery; M Mustard; SY Soy; SD Sulphur Dioxide; ML Molluscs; SE Sesame; CR Crustacean; G Gluten; P Peanuts
Farmers Market Terrace · 19:30–21:00 | Menus | BeGood / Six Senses | Needs Confirmation |  |  |  | Aream & Co. Team Dinner; Italian/Orchard à la carte; guarantee 20 guests; note: ADD IN CREW DINNER HERE IN HORIZON HOUSE
HORIZONS House · 12:00–19:00 | Menus | BeGood / Six Senses | On Track |  |  |  | Cold towels; welcome drinks; light lunch 11:00–13:00 for 40 pax; buffet lunch 13:00–14:30 for 30 pax; afternoon food 15:00–17:00 for 30 pax
Pool Deck & Beach · drinks 19:00–20:00; BBQ dinner 20:00–22:00 | Menus | BeGood / Six Senses | On Track |  |  |  | First evening drinks reception 170 pax; BBQ dinner 150 pax; late snacks Speakeasy/Arcade/Tournament 23:30–01:00 for 70 pax
Breakfast Partel & Pharmacy 07:00–09:30; coffee break HORIZONS Hall/Orchard 11:30–12:00; lunch Partel & Pharmacy 13:00–14:30 | Menus | BeGood / Six Senses | On Track |  |  |  | Breakfast menu; coffee break 150 pax; lunch 170 pax; rolling refreshments Cliffhanger Mansion 14:15–18:15 for 10 pax
Dinner drinks 19:30–22:30; Beach Caves/Orchard/Farmers Market Terrace; late snacks 23:30–01:00 | Menus | BeGood / Six Senses | On Track |  |  |  | Mobile Consumer dinner Beach Caves 100 pax; PC Console + Aream Internal Orchard/Market Terrace 50+20 pax; Speakeasy/Arcade/Poker late snacks 75 pax
Breakfast Farmers Market & Orchard 07:00–09:30; coffee break Orchard/Cinema 11:00–11:15; lunch Pool Deck 12:00–13:30 | Menus | BeGood / Six Senses | On Track |  |  |  | Breakfast menu; coffee break 90/50 pax; Pool Deck lunch 170 pax; entertainment line included in menu
Gala dinner drinks Partel and Pharmacy 19:00–22:00; pre-dinner canapés 19:30–20:00; Gala Dinner Partel & Sun Deck 20:00–22:00; afterparty snacks HORIZONS House 23:30–01:30 | Menus | BeGood / Six Senses | On Track |  |  |  | Gala dinner 170 pax; extra drinks 75 pax after 22:00; afterparty snacks 75 pax
Farmers Market & Orchard · 07:00–09:30 | Menus | BeGood / Six Senses | On Track |  |  |  | Breakfast menu similar to Thursday; final morning F&B
Ben Eddon-Carruthers | Menus | BeGood / Six Senses | On Track |  |  |  | Agency: BeGood; Dietaries: None listed; Arrival: 07 Jun 2026; Departure: 13 Jun 2026
Cheryl Leno | Menus | BeGood / Six Senses | On Track |  |  |  | Agency: BeGood; Dietaries: None listed; Arrival: 07 Jun 2026; Departure: 13 Jun 2026
Nikki Mathias | Menus | BeGood / Six Senses | On Track |  |  |  | Agency: BeGood; Dietaries: None listed; Arrival: 07 Jun 2026; Departure: 13 Jun 2026
Rose Butler | Menus | BeGood / Six Senses | On Track |  |  |  | Agency: BeGood; Dietaries: None listed; Arrival: 08 Jun 2026; Departure: 13 Jun 2026
Libby Laurie | Menus | BeGood / Six Senses | On Track |  |  |  | Agency: BeGood; Dietaries: None listed; Arrival: 08 Jun 2026; Departure: 13 Jun 2026
Liz Morris | Menus | BeGood / Six Senses | On Track |  |  |  | Agency: BeGood; Dietaries: None listed; Arrival: 07 Jun 2026; Departure: 13 Jun 2026
Chris Manoe | Menus | BeGood / Six Senses | On Track |  |  |  | Agency: I.N.C; Dietaries: No Fish; Arrival: 07 Jun 2026; Departure: 12 Jun 2026
Samuel Hosier | Menus | BeGood / Six Senses | On Track |  |  |  | Agency: I.N.C; Dietaries: None listed; Arrival: 08 Jun 2026; Departure: 12 Jun 2026
Tamy Hosier | Menus | BeGood / Six Senses | On Track |  |  |  | Agency: I.N.C; Dietaries: None listed; Arrival: 08 Jun 2026; Departure: 12 Jun 2026
Dean Whitehead | Menus | BeGood / Six Senses | On Track |  |  |  | Agency: I.N.C; Dietaries: No Fish. No Cheese; Arrival: 08 Jun 2026; Departure: 12 Jun 2026
Final printable call sheets | Call Sheets | TBC | File Needed |  |  |  | File needed. Add final upload/link when available.
Venue map pack | Maps | TBC | File Needed |  |  |  | File needed. Add final upload/link when available.
Final seating plans | Seating Plans | TBC | File Needed |  |  |  | File needed. Add final upload/link when available.
Room layout pack | Room Layouts | TBC | File Needed |  |  |  | File needed. Add final upload/link when available.
Final print files | Print Assets | TBC | File Needed |  |  |  | File needed. Add final upload/link when available.
Final signage print files | Signage / Easel Boards | TBC | File Needed |  |  |  | File needed. Add final upload/link when available.
Supplier confirmations | Supplier Docs | TBC | File Needed |  |  |  | File needed. Add final upload/link when available.
Stage/AV technical pack | Stage / Technical | TBC | File Needed |  |  |  | File needed. Add final upload/link when available.
Final travel manifest | Travel / Flights | TBC | File Needed |  |  |  | File needed. Add final upload/link when available.
StudioBinder call sheet example | Call Sheet / Production | Samuel Price | File Needed |  |  |  | Call sheet layout reference
Current production call sheet | Call Sheet / Production | Samuel Price | File Needed |  |  |  | Production operations
Weather call sheet reference | Call Sheet / Production | Samuel Price | File Needed |  |  |  | Weather module
Final master schedule | Call Sheet / Production | Samuel Price | File Needed |  |  |  | Schedule approval
Ben’s document | Call Sheet / Production | Ben Eddon-Carruthers | File Needed |  |  |  | Operations detail
Production contact hierarchy | Call Sheet / Production | Samuel Price | File Needed |  |  |  | Who Do I Call
Crew call sheet layout | Call Sheet / Production | Samuel Price | File Needed |  |  |  | Printable call sheet
Cvent agenda export | Cvent / Event App | Samuel Price | File Needed |  |  |  | Cvent comparison
Cvent speaker/session export | Cvent / Event App | Samuel Price | File Needed |  |  |  | Cvent comparison
Cvent venue/location list | Cvent / Event App | Samuel Price | File Needed |  |  |  | Cvent comparison
Cvent meal/restaurant schedule | Cvent / Event App | Samuel Price | File Needed |  |  |  | Cvent comparison
Cvent attendee-facing copy | Cvent / Event App | Samuel Price | File Needed |  |  |  | Cvent comparison
Speaker list | Speaker / Deck Content | Samuel Price | File Needed |  |  |  | Speaker content
Speaker bios | Speaker / Deck Content | Samuel Price | File Needed |  |  |  | Deck creation
Speaker session titles | Speaker / Deck Content | Samuel Price | File Needed |  |  |  | Website/Cvent comparison
Speaker session descriptions | Speaker / Deck Content | Samuel Price | File Needed |  |  |  | Deck creation
Speaker deck copy | Speaker / Deck Content | Samuel Price | File Needed |  |  |  | Deck creation
Speaker notes | Speaker / Deck Content | Samuel Price | File Needed |  |  |  | Call sheet
Speaker rehearsal schedule | Speaker / Deck Content | Dawn Ramsden | File Needed |  |  |  | Rehearsals
Horizons Hall rehearsal schedule | Speaker / Deck Content | Dawn Ramsden | File Needed |  |  |  | Rehearsals
HORIZONS_MASTER_EVENT_CONTROL_UPDATED.xlsx | Source Data | Samuel Price | Added to Website |  |  |  | Master event control workbook generated and saved in final files folder.
HORIZONS_CONTACTS_AND_WHO_DO_I_CALL.xlsx | Source Data | Samuel Price | Added to Website |  |  |  | Phone-ready contact and escalation workbook generated.
HORIZONS_SLACK_SETUP_GUIDE_UPDATED.md | Slack | Samuel Price | Added to Website |  |  |  | Slack setup guide with channels and environment variable placeholders.
Horizons Style Guide.pdf | Style Guide | Samuel Price | Reference |  |  |  | Official brand/style guide reference.
Horizons Swag Delivery Brief.pdf | Swag / Guest Materials | Samuel Price | Reference |  |  |  | Swag and room drop delivery reference.

## SOURCE_ARCHIVE
Source archive. Old data is archived, not deleted.
Source File | Type | Date Added | Key Information Captured | Related Master Tabs | Related Website Sections | Status | Notes
content.json | JSON | 2026-05-29 | Official website display data and records | All website tabs | All website sections | Current | Exported into final files.
HORIZONS_Website_Update_Tracker.xlsx | XLSX | 2026-05-29 | Website change requests and approved update intake | MASTER_CHANGELOG / AUDIT_LOG | Website workflow | Current | Control workbook retained.
HORIZONS_Missing_Info_Questions_Tracker.xlsx | XLSX | 2026-05-29 | Missing questions/assets/contact gaps | MISSING_FILES_TRACKER | Missing Files | Current | Team-facing tracker retained.
HORIZONS_Website_Final_Schedule_Sync_For_Codex.xlsx | XLSX | 2026-05-29 | Latest final schedule sync used for website data | MASTER_SCHEDULE / LOCATION_SCHEDULES | Schedule / Call Sheet | Source | Backed up before this pass.
Horizons Website & Runbook.pdf | PDF | 2026-05-29 | Runbook and revision reference | DAILY_RUNBOOK / SOURCE_ARCHIVE | Runbook / Operations | Source | Archived as reference.
Horizons Style Guide.pdf | PDF | 2026-05-29 | Brand system and style rules | DOCUMENTS_LINKS / SOURCE_ARCHIVE | Brand / Logos | Source | Linked in document library.
Horizons Swag Delivery Brief.pdf | PDF | 2026-05-29 | Swag, room drop, and materials references | GUEST_MATERIALS_EXPERIENCE | Materials / Room Drops | Source | Linked in document library.
slack-config.example.json | JSON | 2026-05-29 | Slack channel/event mapping without credentials | SLACK_SETUP | Slack | Current | No secrets included.

## AUDIT_LOG
Audit log for major changes.
Date | Updated By | File / Tab Updated | Change Made | Reason | Source | Status | Notes
2026-05-29 | Codex | TEAM_CONTACTS | Added explicit contact phone/WhatsApp details | Make contacts easy to find | User provided contact list | Complete | Samuel Price and Samuel Hosier kept separate.
2026-05-29 | Codex | WHO_DO_I_CALL | Created problem-first escalation guide | Fast onsite decisions | User brief | Complete | Added to website records.
2026-05-29 | Codex | MASTER_SCHEDULE | Mapped current website schedule into master tabs | Single source of truth | content.json | Complete | Old/source references retained in SOURCE_ARCHIVE.
2026-05-29 | Codex | LOCATION_SCHEDULES | Separated location schedule records | Boss requested location-specific views | content.json | Complete | Location details remain expandable.
2026-05-29 | Codex | RESTAURANT_SCHEDULES | Separated restaurant/meal schedules | Restaurants should work like locations | content.json | Complete | Menu gaps remain File Needed.
2026-05-29 | Codex | PODCAST_SCHEDULE | Separated podcast schedule | Podcast needs dedicated view | content.json | Complete | Unknown guests remain TBC/Needs Confirmation.
2026-05-29 | Codex | ENTERTAINMENT_SCHEDULE | Separated entertainment records | Performer views requested | content.json | Complete | Riders/timings still need confirmation.
2026-05-29 | Codex | CURATED_PLAYLISTS | Separated playlist cue records | Music ownership requested | content.json | Complete | Playlist links still needed.
2026-05-29 | Codex | DOCUMENTS_LINKS | Created document library exports | Files should be easy to locate | content.json/source files | Complete | Missing files marked File Needed.
2026-05-29 | Codex | SLACK_SETUP | Added Slack setup records and example config | Website source of truth, Slack alerts layer | User brief | Complete | No webhook URLs committed.
2026-05-29 | Codex | Brand naming | Confirmed Aream & Co. and BeGood spelling | Brand cleanup | User brief | Complete | Incorrect variants removed from live data.
2026-05-29 | Codex | Backup | Created dated backup before edits | Protect all prior work | Filesystem snapshot | Complete | Backup stored in desktop HORIZONS folder.